## Safety Risk Log
1. BASIC RISK INFORMATION | [8 empty] | 2. RISK ASSESSMENT | [8 empty] | 3. RISK RESPONSE | [5 empty] | 4. RISK TRACKING/PROGRESS
Risk # | Date Risk First Reported | Activity Description | Hazard Description | Last RISK Update M/D/Y | Impact Description (Consequence) | Name Current Controls |  |  | Severity 1-4 | Probability 1-5 | Risk Value Severity x Probability |  | Is Risk Level Acceptable? Y/N | Additional Specific Controls |  |  | Is Risk Level Acceptable Now? Y/N | Permanent Solution | Cost of Solution $ | Cost if No Action Taken | Responsible Party | Target Completion Date | Dept. Mgmt. Approval | Completed Actions | Planned Future Actions | Risk Status Open / Completed / Moved to Issue
[6 empty] | Engineering | Administrative | PPE | [5 empty] | Engineering | Admin | PPE
R 1 | 2011-02-10 | Procedures for LOTO still have not been implemented (problem not a description) |  | 2011-06-01 | Some could be injured because a source of energy was not under conttrol |  |  |  | 4 | 3 | 12 | FALSE | [6 empty] | 500 |  |  | 2011-08-01 | Adm | Procedure is written, but locks, tags and boxes not purchased. (not in budget) | 1. Budget for LOTO Implementation in 2012. 2. Purchase locks tags and boxes in CY 2012. 3. Implement LOTO by mid year | Open
R 2a | 2011-04-21 | Need Scissors lift for grounds keepers to get to tall hedges north of admin bldg. |  | 2011-06-01 | Some could be injured because of a fall from a ladder |  |  |  | 4 | 2 | 8 | TRUE | [6 empty] | 30000 |  |  |  | Acceptance | Scissors lift not in budget. | 1. Budget for scissors lift in 2012. 2. Lease lift in CY 2012. 3. Make employees aware of hazards of ladders | Open
R 2b | 2011-04-21 | Need Scissors lift for grounds keepers to get to tall hedges north of admin bldg. |  | 2011-06-01 | Some could be injured because of a fall from a ladder |  |  |  | 4 | 2 | 8 | [7 empty] | 1000 |  |  | 2011-09-01 | Adm | Initiate ladder training Always have one person holding the ladder.
R 3 | Ongoing | Chemical Burns |  | 2011-01-15 | We use 15 different hazardous chemicals, any of which could be spilled causing burns. |  |  |  | 2 | 3 | 6 | FALSE | [6 empty] | 10000 |  |  | Ongoing | PPE/Adm | 1. Written HAZCOM Program in place 2. Employees trained 3. Chemical containers are labeled. | 1. Annual refresher training | 2012-04-05
R 4 | Ongoing | Chemical Spills |  | 2011-01-15 | We use 15 different hazardous chemicals, any of which could be spilled resulting in environmental cleanup issues. |  |  |  | 2 | 3 | 6 | FALSE | [6 empty] | 10000 |  |  | Ongoing | PPE/Adm | 1. Written HAZCOM Program in place 2. Employees trained 3. Chemical containers are labeled. | 1. Annual refresher training | 2012-04-05
R 5 | [11 empty] | FALSE
R 6 | [11 empty] | FALSE
R 7 | [11 empty] | FALSE
R 8 | [11 empty] | FALSE
R 9 | [11 empty] | FALSE
R 10 | [11 empty] | FALSE
R 11 | [11 empty] | FALSE
R 12 | [11 empty] | FALSE
R 13 | [11 empty] | FALSE
R 14 | [11 empty] | FALSE
R 15 | [11 empty] | FALSE
R 16 | [11 empty] | FALSE
R 17 | [11 empty] | FALSE
R 18 | [11 empty] | FALSE
R 19 | [11 empty] | FALSE
R 20 | [11 empty] | FALSE
R 21 | [11 empty] | FALSE
R 22 | [11 empty] | FALSE
R 23 | [11 empty] | FALSE
R 24 | [11 empty] | FALSE
R 25 | [11 empty] | FALSE
R 26 | [11 empty] | FALSE
R 27 | [11 empty] | FALSE
R 28 | [11 empty] | FALSE
R 29 | [11 empty] | FALSE
R 30 | [11 empty] | FALSE
R 31 | [11 empty] | FALSE
R 32 | [11 empty] | FALSE
R 33 | [11 empty] | FALSE
R 34 | [11 empty] | FALSE
R 35 | [11 empty] | FALSE
R 36 | [11 empty] | FALSE
R 37 | [11 empty] | FALSE
R 38 | [11 empty] | FALSE
R 39 | [11 empty] | FALSE
R 40 | [11 empty] | FALSE
R 41 | [11 empty] | FALSE
R 42 | [11 empty] | FALSE
R 43 | [11 empty] | FALSE
R 44 | [11 empty] | FALSE
R 45 | [11 empty] | FALSE
R 46 | [11 empty] | FALSE
R 47 | [11 empty] | FALSE
R 48 | [11 empty] | FALSE
R 49 | [11 empty] | FALSE
R 50 | [11 empty] | FALSE
R 51 | [11 empty] | FALSE
R 52 | [11 empty] | FALSE
R 53 | [11 empty] | FALSE
R 54 | [11 empty] | FALSE
R 55 | [11 empty] | FALSE
R 56 | [11 empty] | FALSE
R 57 | [11 empty] | FALSE
R 58 | [11 empty] | FALSE
R 59 | [11 empty] | FALSE
R 60 | [11 empty] | FALSE
R 61 | [11 empty] | FALSE
R 62 | [11 empty] | FALSE
R 63 | [11 empty] | FALSE
R 64 | [11 empty] | FALSE
R 65 | [11 empty] | FALSE
R 66 | [11 empty] | FALSE
R 67 | [11 empty] | FALSE
R 68 | [11 empty] | FALSE
R 69 | [11 empty] | FALSE
R 70 | [11 empty] | FALSE
R 71 | [11 empty] | FALSE
R 72 | [11 empty] | FALSE
R 73 | [11 empty] | FALSE
R 74 | [11 empty] | FALSE
R 75 | [11 empty] | FALSE
R 76 | [11 empty] | FALSE
R 77 | [11 empty] | FALSE
R 78 | [11 empty] | FALSE
R 79 | [11 empty] | FALSE
R 80 | [11 empty] | FALSE
R 81 | [11 empty] | FALSE
R 82 | [11 empty] | FALSE
R 83 | [11 empty] | FALSE
R 84 | [11 empty] | FALSE
R 85 | [11 empty] | FALSE
R 86 | [11 empty] | FALSE
R 87 | [11 empty] | FALSE
R 88 | [11 empty] | FALSE
R 89 | [11 empty] | FALSE
R 90 | [11 empty] | FALSE
R 91 | [11 empty] | FALSE
R 92 | [11 empty] | FALSE
R 93 | [11 empty] | FALSE
R 94 | [11 empty] | FALSE
R 95 | [11 empty] | FALSE
R 96 | [11 empty] | FALSE
R 97 | [11 empty] | FALSE
R 98 | [11 empty] | FALSE
R 99 | [11 empty] | FALSE
R 100 | [11 empty] | FALSE
Note on A2: Note: Provide a unique identifier for risk
Note on C2: Note: A risk event statement states: (i) what might happen in the future and (ii) its possible impact on the project. ("Weather" is not a risk event statement. "Bad weather may delay the project" is a risk event statement.)
Note on D2: Note: A risk event statement states: (i) what might happen in the future and (ii) its possible impact on the project. ("Weather" is not a risk event statement. "Bad weather may delay the project" is a risk event statement.)
Note on E2: Note: Enter: The date the risk (not the entire log) was updated
Note on F2: Note: List the specific impact the risk could have on the project schedule, budget, scope, and quality. Other impacts can also be listed
Note on K2: Severity Note: Enter # 1 - 4 for degree of severity that this risk could result in - 4 = greatest risk
Note on L2: Probability: Enter # 1 - 5 for the degree of probability. 1 being the least likely to occur and 5 being the most likely to occur
Note on M2: Note: Calculation: F x H
Note on P2: Additional Controls: If the risk level is unacceptable with current controls, what additional controls can you implement to reduce the risk level? Enter each type of control if applicable
Note on S2: Addt'l Controls: With additional controls added, will the risk now be acceptable?
Note on V2: Note: Record the estimated cost of the remedy. This may impact the timeline.
Note on W2: Note: This would be the cost to the company if no action is taken to remedy the hazard.
Note on Y2: Note: Enter the date this item is supposed to start.
Note on Z2: Note: Enter: PPE, Adm, Eng, Avoid, Remove, Substitute, Transfer, Insure (purchase/self) Acceptance=will live with the risk
Note on AB2: Note: List, by date, all actions taken to respond to the risk. (this does not include assessing the risk)
Note on AC2: Note: List, by date, what will be done in the future to respond to the risk
Note on AD2: Note: State if risk is: open (still might happen and still has to be managed); date completed (has passed or has been successfully mitigated); moved to issue (risk has happened)